## Resource Mob Plan
NMAC Resource Mobilization Action Plan Worksheet
February 2016
GENERAL ACTIVITIES | Required Resource Mobilization Plan Tasks | Direct Actors | Resource Mobilization Responsible Person | Periodicity | Indication on Budget Required to Achieve Target | Remarks | Priority (high, medium, low)
or time line
Coordination
Coordination between NMAC, Government Ministries & Departments | One annual national steering committee meeting: Colombo | Key ministries: MPRRRHRA, MOD, MFA, Health, Agriculture, Social Welfare, Housing + stakeholders on invitation | NMAC Director (DIR) | Annually | Logistics cost of meeting | NMA+G6:G20
| Three annual regional steering committee meetings: 3 regions - East, North, Centre North | NMAC, RMAO, District Secretariat | NMAC Assistant Director (AD) / RMAO | Annually | Logistics cost of meetings | -
| Circulate calendar of meetings, agenda and meeting notes | NMAC | NMAC AD | after each meeting | - | -
Coordination NMAC, stakeholders and donors relation | Operational committee meeting: national level | NMAC, RMAO, HD operators, MRE, VA, Ministries, UN others | NMAC DIR / AD | Bi-annually | Logistics cost of meetings | Annual mine action workplan and its review 6 months later: Colombo
| Operational committee meetings: district level | NMAC, RMAO, HD operators, MRE, VA, District secretariats, UN | RMAO, NMAC AD | Monthly for HD & Quarterly for VA & MRE | Operational planning workshop in RMAO or district secretariat on rotational basis: logistics cost of meetings | districts could be clubbed together according to requirements
| Regular meetings with donors in Colombo: present strategy and progress | NMAC, Embassies, UN agencies | NMAC DIR | Bi-annually | Logistics cost of meetings | Reactivate MA support group in SL (MASG SL)
| Develop Donor data base: collect and centralize information : funding cycles, policy and strategy, contact persons in Embassy and their ministries | NMAC | NMAC AD | Continuously | - | -
| Introduce MA to corporate sector | NMAC, Stakeholders | NMAC DIR | - | - | Invite corporate sector to events such as 4th of April
Communication
Communication plan | NMAC to develop a communications and marketing plan | NMAC | NMAC AD + COM | 2016 | - | -
Consistent messaging | Collect information, sector news, progress, difficulties fom all operators during operational committee meetings | All sector operators and stakeholders | NMAC AD + COM + RMAO | Continuously | - | Survey results, major events, and progress towards strategy outcomes
| Develop messages for dissemination | NMAC COM | NMAC AD + COM | Continuously | - | -
| Coordination of communication for ministries involved, media monitoring role | NMAC | NMAC DIR + COM | Continuously | - | Avoid dissemination of confusing messages
Marketing of the sector | Develop marketing tools and channel: NMAC website, Facebook page, Newsletter | NMAC | NMAC AD + COM | Continuously/ E-mail Newsletter quaterly | Costs for website creation and maintenance | -
| Messaging through social media, TV/Radio, newspaper, others | NMAC | NMAC AD + COM | Continuously | media budget from NMAC | -
| Communicate the new GoSL's increased interest in the sector & measures taken to support operators | All stakeholders | NMAC + Operators | Continuously | - | Government support to the sector/ operators should be more visible
| 4th of April: International Day of Mine Awareness and Assistance | NMAC and all operators, civil society | NMAC DIR + AD , RMAO, | Annually | events and media budget | -
| Field visit for various audiences: media and donors | NMAC, RMAO | - | Annually | logistics costs | cost-sharing with operators possible
| Visit Embassies individually to present progress and needs | NMAC Director and Embassies | NMAC DIR + AD | Once year minimum | - | -
| Special event to advertise the signature of the Ottawa Treaty | NMAC, MPRRRHRA, all stakeholders | NMAC DIR | When officially signed | - | -
| 5-year national strategy and mid-term review: tool for communication | NMAC | NMAC DIR | Twice in 5 years | budget with 2020 as target to complete the work | NMAC annual internal review and update
| Select a prominent 'ambassador' for mine action and develop a communiation plan | NMAC | NMAC DIR | asap | - | Cricket player, movie star
| Regular communication with Sri Lankan Embassies overseas through MFA | NMAC | NMAC DIR+AD | Continuously | - | SL Embassies to promote support for MA
NMAC Resources/ Capacity
Coordination capacity within NMAC | Create a position and recruit professional staff for the coordination of Operations and mine risk education activities (OPS/MRE) activities | NMAC | NMAC Director (DIR) + AD | Q1 2016 | government pay scale | Approach Ministry, and/or donors locally and/or UN to finance or second professional staff. a/ For COM and OPS/MRE positions b/For VA position Handicap International proposed to second a professional staff. To be confirmed
| Create a position and recruit or get the secondment of a professional staff for the coordination of VA activities | NMAC | NMAC Director (DIR) + AD | Q1 2016 | government pay scale
Communication and coordination capacity within NMAC | Create a position and recruit professional staff for coordination and communications (COM) | NMAC, MPRRRHRA | NMAC DIR | Q1 2016 | government pay scale
Traditional donors/international cooperation | Obtain in-kind support for the pillars of the sector | All operators, Embassies' military attaches, INGOs | NMAC AD | - | - | Donation of equipment, expert human resources
Funds diversification | Develop new ideas for resource mobilisation such as crowd sourcing, partnership with corporate sector | NMAC, all operators | NMAC AD + COM | Continuously | - | Example Lebanon: partnership with Bank
Government funding | Creation of special Trust fund and offer of matching funds | NMAC, Donors | NMAC DIR | 2016 | - | See model of Trust funds
| Message to MoD and MoF to increase funding for HD by Engineers | NMAC | NMAC DIR | 2016 | - | -
Strategic plan 2016 -2020
Strategic Objective 1 HD | Budget projection for HD Operators : NTS, TS, Clearance | NMAC, HD Operators | NMAC DIR + AD | Annually for 5 years | Estimate 2015 total Budget for HD operators: 5.5 million US$. To be confirmed by NMAC | It is to be noted that with the total budget of 2015 (NGOs+ Engineers) approximately 6,5 km2 have been cleared and reduced in 2015. To cover the estimated 64 km2 double resources are approximately needed every year to complete the work in 5 years by 2020. However these estimated figures can change once the re-survey is completed.
| Budget projection for Military Engineers HD unit | NMAC, MOD | NMAC DIR + AD | Annually for 5 years | Estimate 2015 Total Budget for Military Engineers HD unit: 0.5 million US$ To be confirmed by NMAC
| Develop proposals for donors with NMAC support | HD Operators | NMAC AD | Continuously | - | based on national srategy and on annual work plans
| Report to donors | HD Operators, NMAC | NMAC AD | Continuously | - | -
| Communicate additional progress and achievements to donors | Hd Operators, NMAC | NMAC DIR + AD | Continuously | - | -
Strategic Objective 2 MRE | Budget projection for MRE sector | NMAC, UNICEF, Ministry of Education | NMAC DIR + AD | Annually for 5 years | Budget 2015 as baseline; increase for 2016 according to staff coverage requirements | Estimate 2015 total budget for MRE
| Develop proposals for donors with NMAC support | MRE Operators | NMAC DIR + AD | Continuously | - | estimate additional activities required and human resources needed
| Report to donors | MRE Operators, NMAC | NMAC AD | Continuously | - | -
| Communicate progress and achievements to donors | MRE Operators, NMAC | NMAC DIR + AD | Continuously | - | -
Strategic Objectif 3 VA | Collect information and statistics from competent sources and identify needs | NMAC, UNICEF, Ministry of Health, ICRC | - | - | - | -
| NMAC to follow up with relevant ministries on the provision and access to existing services for: physical rehabilitation, prosthesis and orthosis, social and psychosocial support | MoH, MoSS, NMAC, Handicap International, ICRC, UNICEF | NMAC VA/MRE Officer | Continuously | Mainstreaming in Surthi program, disability fund | -
| Develop proposals for donors with NMAC support | VA Operators | NMAC VA/MRE Officer | Continuously | - | estimate additional activities required and human resources needed
| Report to donors | VA Operators, NMAC | NMAC AD + VA/MRE Officer | Continuously | - | -
| Communicate additional progress and achievements to donors | VA Operators, NMAC | NMAC VA/MRE Officer | Continuously | - | -
Strategic Objectif 4 APMBC | Follow up on GoSL endorsement of the APMBC and official announcement | NMAC, ICBL, all Operators, ISU | NMAC DIR | 2016 | - | -
Strategic Objective 5 Residual Contamination | Study the long term requirements for the management of residual contamination | NMAC, MOD, HD Operators, GICHD | NMAC DIR | 2017 | Budget projection as part of study | -
Strategic Objective 6 IM | Integrate national data management requirements in government budget | NMAC, GoSL | NMAC DIR + IM | - | - | -
| Develop proposal for donors for financial and in-kind support | NMAC Information Management (IM), all operators, GICHD | NMAC IM | - | - | -